ONR Technical Inspection Guide (TIG) LC19 – Construction or installation of new plant

Contents

1.	Introduction	3

2.	Licence Condition 19 – Construction or installation of new plant	4

3.	Purpose and outcomes of Licence Condition 19	5

3.1.	Outcomes and applicability	5

4.	Guidance on inspection of Licence Condition 19	7

4.1.	Arrangements	7

4.2.	Inspection of implementation of arrangements	11

4.3.	Consultation with other regulators	13

5.	Safeguards requirements	13

References	14

Document control information	15

# Introduction

Technical Inspection Guides (TIG) support inspectors undertaking compliance inspections to make regulatory judgements in relation to the adequacy of compliance and in providing regulatory advice on specific Licence Conditions (LCs) to licensees. LC19 sits within a suite of licence conditions (LC19–22 and LC35) that together establish a rigorous and proportionate framework for the regulatory control of change, providing control at the construction and installation stage of the plant lifecycle ahead of modification, commissioning, operation and decommissioning.

The purpose of this guidance is to facilitate a consistent approach to LC19. While not exhaustive or mandatory, the guidance offers a clear framework for inspectors to assess the adequacy of compliance. Inspectors should also refer to the ONR policy on Risk-Informed and Targeted Engagements (RITE) [1], which guides risk-based prioritisation in regulatory interventions and supports decisions on engaging with dutyholders.

# Licence Condition 19 – Construction or installation of new plant

- The LC states:

“19(1)   Where the licensee proposes to construct or install any new plant which may affect safety the licensee shall make and implement adequate arrangements to control the construction or installation.

19(2)	   The licensee shall submit to ONR for approval such part or parts of the aforesaid arrangements as ONR may specify.

19(3)   The licensee shall ensure that once approved no alteration or amendment is made to the approved arrangements unless ONR has approved such alteration or amendment.

19(4)	   The licensee shall, if so directed by ONR, carry out a review and reassessment of safety and submit a report of such review and reassessment to ONR at such intervals, within such a period and for such of the matters or operations as may be specified in the direction.

19(5)    The licensee shall, if so, directed by ONR, halt the construction or installation of a plant and the licensee shall not recommence such construction or installation without the consent of ONR” [2].

Note: Specifications, Approvals, Directions, and Specifications under 
LC 19(2),(3), and (4) are rare; most LC19 permissions are regulated via derived powers under the licensee’s arrangements.

# Purpose and outcomes of Licence Condition 19

The purpose of this licence condition is to require that the licensee exerts rigorous control over the construction or installation of any new plant that may affect safety, ensuring it complies with the approved nuclear safety case. While LC19 does not explicitly evaluate the safety case or design, it requires that arrangements are linked to LC14, so each stage’s safety is demonstrated before activities commence. Any modifications to the design of plant under construction, in accordance with LC19 arrangements, shall be progressed under arrangements made under LC20.

## Outcomes and applicability

### Outcomes

The main LC19 regulatory outcomes being sought are:

Construction and Installation activities are rigorously and effectively controlled to ensure nuclear safety.

Plant is constructed in accordance with the approved safety case.

Nuclear safety is demonstrated at each defined stage prior to the activities being undertaken.

Effective change control arrangements are in place during construction to ensure that modifications are subject to proportionate assessment, governance, and approval prior to implementation. (See also LC20).

Arrangements are embedded within the management system, maintained as current and reviewed at appropriate intervals.

### Conventional Health and Safety

The regulation of CH&S (NS H&S) aspects (e.g. CDM), are not included within LC19, but are intrinsically linked. Inspectors should thus refer to ONR guidance on:

NS-INSP-GD-074 Construction (Design and Management). [3]

NS-TAST-GD-49 Licensee Core Safety and Intelligent Customer Capabilities. [4]

NS-INSP-GD-073 -The Regulation of Life Fire Safety on Nuclear Licensed Sites. [5]

### Security

Aspects of new plant construction or installation are excluded from LC19; inspectors should instead refer to the relevant SyAPs, particularly SyDP 6.6 – Nuclear Construction Sites.

# Guidance on inspection of Licence Condition 19

## Arrangements

In judging the adequacy of the arrangements consider:

To ensure effective compliance with this LC, the licensee must establish arrangements, process/procedures, that provide assurance of addressing all legal requirements set out in sections (1) to (5) of this condition.

The arrangements are documented within the licensee’s safety management system, current and authorised by an appropriate SQEP individual.

Use LC14 arrangements to produce and assess safety case documentation covering all lifecycle stages.

Ensure the safety case is sufficiently mature before each construction or installation stage begins; complex projects may require sub-division (e.g. civil structures and facility installation).

Confirm the safety case is adequately developed to demonstrate that the detailed design will meet safety objectives prior to construction or installation (refer also to NS-TAST-GD-051 [6]).

The arrangements maintain the integrity of the justified design during construction and installation, including effective management of technical queries, non-conformances and omissions; design changes must be controlled under LC20.

Arrangements address the impact of new plant construction or installation on the safety case of an existing installation and its continued validity. These arrangements should also manage any impacts on the extant safety case using LC22 arrangements.

Where construction or installation occurs on a nearby licensed site, ensure appropriate liaison with the affected licensee to manage safety impacts.

Arrangements should provide for the preservation of completed structures and installed equipment until commissioning or formal transfer of responsibility to operations.

LC19 arrangements should, where appropriate, stage construction or installation with defined hold points and recognise ONR’s power to require consent before commencing or progressing between stages under LC19(4). ONR may opt to permission all or only selected stages of the construction or installation

Arrangements should allow ONR flexibility in permissioning by providing derived powers to agree or acknowledge commencement or progression between construction or installation stages.

Table 1 - Interdependency with other LC’s / legislation

| - LC / legislation | - Intent / purpose | - LC19 Interdependency | - Regulatory outcome |
| --- | --- | --- | --- |
| - LC6 Documents, Records, Authorities and Certificates | - Ensure adequate records and documentation are produced, controlled and retained to demonstrate safety. | - LC19 construction and installation activities generate safety-significant records (e.g. build records, test evidence, certificates) that must be captured and controlled. | - Evidence available to demonstrate plant constructed and installed in accordance with the safety case; traceability and auditability of decisions. |
| - LC10 Training | - Ensure personnel are suitably trained to undertake their duties. | - LC19 delivery relies on trained personnel and contractors to safely construct and install plant in line with safety requirements. | - Reduced risk of human error during construction; competent execution of safety-significant activities. |
| - LC12 Duly Authorised and SQEP | - Ensure safety-significant roles are undertaken by SQEP persons. | - LC19 requires SQEP oversight of construction, acceptance of installed plant, and resolution of deviations from design intent. | - Safety-significant decisions during construction are technically robust and appropriately authorised. |
| - LC17 - Management Systems | - Establish and implement effective management systems, including quality, governance and supply-chain | - LC19 activities are delivered through LC17 systems, including quality management, surveillance, contractor control and assurance processes. | - Construction quality assured; supply chain effectively controlled; consistent/ repeatable delivery of safety significant activities. |
| - LC21 – Commissioning | - Ensure commissioning is properly planned, controlled and justified. | - LC19 provides the controlled transition from construction and installation into commissioning activities under LC21. | - Commissioning undertaken on plant that has been correctly constructed and installed; reduced risk of latent defects. |
| - LC36 – Organisational Capability | - Ensure the licensee has adequate organisational capability and resources to deliver safety. | - Effective LC19 delivery depends on sufficient capability to manage construction, contractors, interfaces and governance. | - Construction adequately resourced organisational weaknesses do not undermine safety control. |
| - CDM Regulations | - Ensure health, safety and welfare are effectively managed during construction activities through defined roles, planning and risk control. | - LC19 construction and installation activities must integrate CDM duties with nuclear safety controls, ensuring conventional construction risks are managed alongside nuclear safety requirements. | - Construction risks are effectively controlled; clear coordination between nuclear and conventional safety arrangements; construction activities do not compromise nuclear safety or workforce protection. |
| - Nuclear Industries Security Regulations (NISR) [6] | - Protect nuclear sites, plant and information against security threats. | - LC19 construction activities must incorporate security controls for new plant, systems and contractors. | - New plant and systems are secure by design; security risks managed during construction and installation. |
| - Regulatory Reform (Fire Safety) Order | - Prevent and mitigate fire risks to protect people and assets. | - LC19 construction must implement fire protection features and controls consistent with fire safety requirements. | - Fire hazards controlled during / after construction; fire protection systems installed as intended. |
| - Nuclear Safeguards Act 2018 [7] | - Ensure nuclear material is accounted for and controlled. | - LC19 construction involving safeguards-relevant plant must accommodate material accountancy, measurement and reporting requirements. | - Safeguards obligations met; nuclear material control not compromised by new construction or installation. |

## Inspection of implementation of arrangements

When inspecting the implementation of arrangements the Inspector should:

Inspect arrangements linking construction and installation activities to safety case requirements at each stage, including awareness, access and application of the safety classification system.

Inspect the effectiveness of quality and surveillance arrangements in delivering construction or installation in line with the justified design and required standards, including supply-chain oversight, using a QMS assessed under LC17.

Inspect how design, construction and installation issues are managed, including technical queries, concessions and omissions, to maintain design intent.

Inspect the licensee’s implementation of its arrangements to construct or install any new plant, which may affect safety, including whether:

work has been subject to the licensee’s internal approval or hold point processes before commencement;

responsibilities for securing and maintaining compliance with the nuclear safety case are clearly defined and recognised, including interfaces between licensees and contractors;

appropriate instructions have been written for on-site activities having the potential to impact nuclear safety;

the licensee’s oversight of the contractors’ control and supervision of construction and installation activities is adequate; and,

adequate segregation is in place to limit interaction with nuclear safety related plant.

Inspect readiness to proceed to the next significant construction stage.

Inspect arrangements for the preservation and maintenance of completed structures and installed equipment prior to commissioning or transfer to operations, including protection against degradation and compliance with LC6 record requirements. Inspect whether preservation and maintenance arrangements remain appropriate and effective where significant delays occur.

Inspect arrangements for the retention of documents, records, authorities and certificates relating to construction or installation, in line with LC6.

Further guidance on ONR’s expectations with respect to the purpose, scope and content of safety cases can be found in NS-TAST-GD-051 - The Purpose, Scope and Content of Safety Cases [8].

NS-PER-GD-001 - The Purpose and Use of Permissioning [9],  
provides guidance on primary and derived power permissioning including on the use of enhanced implementation and control (EIM&C).

NS-TAST-GD-017 -  Civil Engineering - Construction Assurance [10],  provides guidance to inform judgements on the adequacy of civil engineering construction assurance arrangements and, more broadly, on arrangements for construction and installation assurance.

## Consultation with other regulators

The inspector should refer to relevant Memoranda of Understanding to ensure that ONR’s regulation of construction or installation is informed by appropriate consultation and liaison with other regulatory bodies, for example; Environment Agency; the Scottish Environment Protection Agency; Natural Resources Wales; the Health and Safety Executive; the Defence Nuclear Safety Regulator etc.

# Safeguards requirements

Regulation 3 of the Nuclear Safeguards (EU Exit) Regulations 2019 (NSR19) makes specific requirements of operators regarding the timeliness of submitting Basic Technical Characteristics (BTC) documents to ONR at different stages of plant construction or alteration. Such BTCs contain safeguards relevant aspects of facility design and their timely submission is the basis for early safeguards engagement with ONR and, if necessary, the IAEA. Where a licensee has proposed to construct a new facility or install new plant equipment, the inspector should contact ONR Safeguards to ensure that the requirements for BTCs in NSR19 have been complied with.

# References

| [1] | ONR, “ONR-RD-POL-002 - Risk Informed and Targeted Engagements,” [Online]. Available: To ONR staff via HOW2 Hub (Internal ONR system). |
| --- | --- |
| [2] | ONR, “Licence Condition Handbook,” [Online]. Available: To ONR staff via HOW2 Hub (Internal ONR system). |
| [3] | NS-INSP-GD-074 Construction (Design and Management). |
| [4] | NS-TAST-GD-49 Licensee Core Safety and Intelligent Customer Capabilities. |
| [5] | NS-INSP-GD-073 -The Regulation of Life Fire Safety on Nuclear Licensed Sites. |
| [6] | HM Government, “The Nuclear Industries Security Regulations 2003”. |
| [7] | HM Government, “Nuclear Safeguards (EU Exit) Regulations 2019”. |
| [8] | NS-TAST-GD-051 - The Purpose, Scope and Content of Safety Cases.. |
| [9] | NS-PER-GD-001 - The Purpose and Use of Permissioning. |
| [10] | NS-TAST-GD-017 - Civil Engineering - Construction Assurance. |

# Document control information

Authored by: Nuclear Safety Inspector

Approved by: Head of Profession – Operational Inspection

Issue: 7.2

Published: March 2026

Next scheduled review: September 2027

Document reference: NS-INSP-GD-019

Record reference: ONRHH-822789359-20466

Revision commentary

| Issue | Description of update(s) |
| --- | --- |
| 7.1 | Routine minor update, with updated references. |
| 7.2 | Minor update – document simplified and duplication removed, no major change to outcomes or intent. |

Any equipment, system, component, structure or facility that is constructed or installed on the licensed site and which may affect nuclear safety e.g. reactors, ventilation systems, supporting infrastructure, fire protection systems etc.